## 1总概算
附表1
总概算执行情况一览表
建设单位：中国船舶集团有限公司第七一八研究所 | [13 empty] | 单位：万元 |  | 总1表
序号 | 工程项目 | 总概算 |  |  |  |  | 实际完成 |  |  |  |  | 尚需投资 |  | 差额 |  | 备注
|  | 合计 | 建筑 | 设备 | 安装 | 其他 | 合计 | 建筑 | 设备 | 安装 | 其他 | 合计 | 其中已列年度计划 | 超支 | 节约
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
| 总计 | 913 | 549 | 193 | 42 | 129 | 602.6581 | 368.6171 | 180.2363 | 4.3997 | 49.4051 |  |  |  | 310.3419
一 | 工程费用 | 742 | 549 | 193 | 0 | 0 | 548.8534 | 368.6171 | 180.2363 | 0 | 0 |  |  |  | 193.1466
（一） | 室内工程 | 727.6 | 534.6 | 193 | 0 | 0 | 548.8534 | 368.6171 | 180.2363 | 0 | 0 |  |  |  | 178.7466
1 | 制氢设备组装车间 | 总概算 合计: 727.6; 总概算 建筑: 534.6; 总概算 设备: 193; 实际完成 合计: 548.8534; 实际完成 建筑: 368.6171; 实际完成 设备: 180.2363 |  |  | 178.7466
（二） | 室外工程 | 总概算 合计: 14.8; 总概算 建筑: 14.8; 实际完成 合计: 0; 实际完成 建筑: 0 |  |  | 14.8
1 | 室外电气工程 | 总概算 合计: 14.8; 总概算 建筑: 14.8; 实际完成 合计: 0; 实际完成 建筑: 0 |  |  | 14.8
（三） | 概算调差 | 总概算 合计: -0.4; 总概算 建筑: -0.4; 实际完成 合计: 0; 实际完成 建筑: 0 |  | 0.4
二 | 设备安装费 | 总概算 合计: 42; 总概算 安装: 42; 实际完成 合计: 4.3997; 实际完成 安装: 4.3997 |  |  | 37.6003
（一） | 室内工程 | 总概算 合计: 42.2; 总概算 安装: 42.2; 实际完成 合计: 4.3997; 实际完成 安装: 4.3997 |  |  | 37.8003
1 | 制氢设备组装车间 | 总概算 合计: 42.2; 总概算 安装: 42.2; 实际完成 合计: 4.3997; 实际完成 安装: 4.3997 |  |  | 37.8003
（二） | 概算调差 | 总概算 合计: -0.2; 总概算 安装: -0.2; 实际完成 合计: 0; 实际完成 建筑: 0 |  | 0.2
三 | 工程建设其他费用 | 92.9 | 0 | 0 | 0 | 92.9 | 49.4051 | 0 | 0 | 0 | 49.4051 |  |  |  | 43.4949
1 | 建设单位管理费 | 总概算 合计: 17.9; 总概算 其他: 17.9; 实际完成 合计: 0; 实际完成 其他: 0 |  |  | 17.9
2 | 前期工作咨询费 | 总概算 合计: 13.3; 总概算 其他: 13.3; 实际完成 合计: 0; 实际完成 其他: 0 |  |  | 13.3
3 | 工程设计费 | 总概算 合计: 38.9; 总概算 其他: 38.9; 实际完成 合计: 17.1113; 实际完成 其他: 17.1113 |  |  | 21.7887
4 | 工程建设监理费 | 总概算 合计: 17.8; 总概算 其他: 17.8; 实际完成 合计: 7.6565; 实际完成 其他: 7.6565 |  |  | 10.1435
5 | 招标代理服务费 | 总概算 合计: 1; 总概算 其他: 1; 实际完成 合计: 0; 实际完成 其他: 0 |  |  | 1
6 | 环境影响咨询费 | 总概算 合计: 2; 总概算 其他: 2; 实际完成 合计: 7.0755; 实际完成 其他: 7.0755 |  | 5.0755
7 | 安全设施及职业卫生评价费 | 总概算 合计: 2; 总概算 其他: 2; 实际完成 合计: 14.3378; 实际完成 其他: 14.3378 |  | 12.3378
8 | 工程造价咨询费 | 总概算 合计: 0; 总概算 其他: 0; 实际完成 合计: 3.224; 实际完成 其他: 3.224 |  | 3.224
四 | 基本预备费 | 总概算 合计: 35.5; 总概算 其他: 35.5; 实际完成 合计: 0; 实际完成 其他: 0 |  |  | 35.5
五 | 调整批复差异 | 总概算 合计: 0.6; 总概算 其他: 0.6; 实际完成 其他: 0

## 2建筑工程
附表2
建筑工程完成情况一览表
建设单位：中国船舶集团有限公司第七一八研究所 | [9 empty] | 单位：万元 |  | 总2表
序号 | 工程项目编号及名称 | 建设性质 | 工程量 |  |  | 结构及层数 | 开竣工日期 |  | 设计概算 | 实际完成 | 质量评定等级 | 备注 | 招标情况
|  |  | 单位 | 设计 | 实际 |  | 开工 | 竣工 |  |  |  |  | 批复 | 实际
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
| 建安工程 总计 | 改造 | 平方米 | 3095.3 | 3095.3 |  |  |  | 549.2 | 368.6171
一 | 建筑工程 | 改造 | 平方米 | 3095.3 | 3095.3 |  |  |  | 549.4 | 368.6171 |  |  | 部分委托公开
（一） | 室内工程 | 改造 | 平方米 | 3095.3 | 3095.3 |  |  |  | 534.6 | 368.6171
1 | 制氢设备组装车间 | 改造 | 平方米 | 3095.3 | 3095.3 | 门式刚架结构/单层，局部三层 | 2022-06-30 | 2022-12-07 | 534.6 | 368.6171 | 合格 | 17# |  | 委托公开
（二） | 室外工程 | [7 empty] | 14.8
1 | 室外电气工程 | [7 empty] | 14.8
（三） | 概算调差 | [7 empty] | -0.4
二 | 设备安装费 | [7 empty] | 42 | 4.3997
（一） | 室内工程 | [7 empty] | 42.2 | 4.3997
1 | 制氢设备组装车间 | [7 empty] | 42.2 | 4.3997
（二） | 概算调差 | [7 empty] | -0.2

## 3设备
附表3
设备配备情况表
建设单位：中国船舶集团有限公司第七一八研究所 | [8 empty] | 单位：万元 |  | 总3表
序号 | 设备类别 | 单位 | 设计 |  | 实际 |  | 多余 |  | 尚缺 |  | 备 注
|  |  | 数量 | 金额 | 数量 | 金额 | 数量 | 金额 | 数量 | 金额
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| 总计 | 套/万元 | 26 | 193 | 46 | 180.2363
A | 工艺设备 | 套/万元 | 26 | 193 | 26 | 147.6106
B | 公用设备 | 套/万元 | 0 | 0 | 20 | 32.6257
D | 待抵扣进项税 | 套/万元 | 0 | 0 | 0 | 0

## 4变更 (hidden)
附表4
重大设计变更一览表
建设单位：中国船舶集团有限公司第七一八研究所 | [6 empty] | 总4表
序号 | 工程项目 | 变动内容 | 变动原因 | 变动后投资增减（+-） | 原设计批准单位日期文号 | 设计变更批准单位日期文号 | 备注
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
本项目不涉及

## 5设备调整 (hidden)
附表5
设备调整明细表
建设单位：中国船舶集团有限公司第七一八研究所 | [7 empty] | 单位：万元 |  | 总5表
序号 | 名称 | 型号 | 规格 | 产地 | 单位 | 原设计 |  | 调整设计 |  | 调整说明
[6 empty] | 数量 | 金额 | 数量 | 金额
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
本项目不涉及
一 | 调增设备
1
2
3
二 | 调减设备
1
2
三 | 国别调整
1
2
四 | 组成调整
1
2
五 | 指标调整
1
2

## 6未完工程 (hidden)
附表6
未完工程项目一览表
建设单位：中国船舶集团有限公司第七一八研究所 |  |  |  |  | 单位：万元 |  | 总6表
序号 | 工程项目编号及名称 | 工程内容 | 单位 | 未完工程量 | 尚需投资 | 未完原因及说明 | 备注
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
本项目不涉及

## 7未完设备 (hidden)
附表7
未完设备一览表
建设单位：中国船舶集团有限公司第七一八研究所 |  |  |  | 单位：万元 |  | 总7表
序号 | 设备名称 | 型号及规格 | 单位 | 数量 | 金额 | 备注
1 | 2 | 3 | 4 | 5 | 6 | 7
本项目不涉及

## 8人员 (hidden)
附表8
人员配备一览表
建设单位：中国船舶集团有限公司第七一八研究所 | [13 empty] | 总8表
序号 | 车间或科室名称 | 设计人数 |  |  |  | 现有人数 |  |  |  | 缺余人数 |  |  |  | 备注
|  | 合计 | 生产工人 | 辅助工人 | 非生产 人员 | 合计 | 生产工人 | 辅助 工人 | 非生产 人员 | 合计 | 生产工人 | 辅助 工人 | 非生产人员
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | XXX厂房

## 9贷款 (hidden)
附表9
项目贷款还贷情况表（财务）
建设单位：中国船舶集团有限公司第七一八研究所 |  |  |  | 总9表
年份 摘要 | 20XX年 | 20XX年 | 20XX年 | 20XX年
一、贷款总额
其中：贷款本金
贷款利息
二、已还贷款
其中：贷款本金
贷款利息
三、贷款余额
其中：贷款本金
贷款利息

## 10决算 (hidden)
附表10
建设项目竣工决算表
建设单位：中国船舶集团有限公司第七一八研究所 |  |  |  | 项目名称：高纯电子气体产业化建设项目
|  |  |  | 20XX年至20XX年 |  | 单位：万元 | 总10表
金额 年份 项目 | 合计 | 20XX年 | 20XX年 | 20XX年 | 20XX年 | 20XX年 | 20XX年
一、建设拨、借款
1、国家拨款
2、开发银行贷款
3、商业银行贷款
4、其他投资借款
5、集团公司自筹
6、企业自筹
7、项目资本
8、项目资本公积
二、建设支出
1、完成投资额
其中：建安投资
设备投资
其他投资
2、待核销基建支出
3、转出投资
三、建设投资效果
1、交付使用固定资产
2、交付使用流动资产
3、递延资产
4、无形资产
5、年末在建工程
6、待核销基建支出
7、转出投资
四、年末建设节余资金

## 11工艺
附表11
工艺设备批复与实施对比表
建设单位：中国船舶集团有限公司第七一八研究所 | [19 empty] | 总11表
序号 | 批复情况 | [9 empty] | 实施情况
| 名称 | 功能及组成 | 主要性能指标 | 单位 | 国别 | 数量 | 投资 (万元) | 招标情况 | 布置位置 | 备注 | 名称 | 功能及组成 | 主要性能指标 | 单位 | 国别 | 数量 | 投资 (万元) | 招标情况 | 布置位置 | 备注
I | 工艺设备 |  |  |  |  | 26 | 193 |  |  |  | 工艺设备 |  |  |  |  | 26 | 147.6106
1 | 通风柜 |  | 尺寸1800mm*850mm*2350mm;风速0.4-0.5m/s；风量2400m³/h | 套 | 国产 | 22 | 33 |  |  |  | 通风柜 |  | 非标 | 套 | 国产 | 22 | 23.8938
2 | 振动测试台 |  | 尺寸（长×宽）：4m×4m，其高度≥400mm；测试台如有拼接，其整体平整度≤0.1mm，水平度≤0.2mm/m；测试台（铸钢件+钢筋混凝土）固有频率≥70Hz | 套 | 国产 | 4 | 160 |  |  |  | 振动测试台 |  | 非标 | 套 | 国产 | 4 | 123.7168
Ⅳ | 待抵扣进项税 | [9 empty] | 待抵扣进项税 | [9 empty] | 402.7308

## 12建筑物
附表12
建（构）筑物批复与实施对比表
建设单位：中国船舶集团有限公司第七一八研究所 | [14 empty] | 总12表
序号 | 名称 | 批复情况 |  |  |  |  | 实施情况
|  | 面积 | 结构型式 | 布局位置 | 招标情况 | 备注 | 面积 | 结构型式 | 布局位置 | 招标情况 | 中标单位 | 验收备案 | 不动产权证书 | 报建及验收情况 | 备注
1 | 制氢设备组装车间 | 3095.3 | 门式刚架结构/单层，局部三层 | 派瑞科技产业园西区 | 委托公开 |  | 3095.3 | 门式刚架结构/单层，局部三层 | 派瑞科技产业园西区 | 委托公开 | 河北省磁县第一建筑安装公司 |  |  | 工程质量评定 建设单位、施工单位、监理单位共同验收合格

## 13公用
附表13
公用设备批复与实施对比表
建设单位：中国船舶集团有限公司第七一八研究所 | [19 empty] | 总13表
序号 | 批复情况 | [9 empty] | 实施情况
| 名称 | 功能及组成 | 主要性能指标 | 单位 | 国别 | 数量 | 投资 (万元) | 招标情况 | 布置位置 | 备注 | 名称 | 功能及组成 | 主要性能指标 | 单位 | 国别 | 数量 | 投资 (万元) | 招标情况 | 布置位置 | 备注
II | 公用设备 |  |  |  |  | 0 | 0 |  |  |  | 公用设备 |  |  |  |  | 20 | 32.6257
[11 empty] | 冷水机 |  | DX-90WS | 台 |  | 1 | 14.6991
[11 empty] | 冷水机 |  | DX-50WS | 台 |  | 1 | 9.9911
[11 empty] | 净水器 |  | 3T | 台 |  | 2 | 1.5044
[11 empty] | 配电箱 |  | AP1 | 台 |  | 1 | 0.21629
[11 empty] | 配电箱 |  | AP2 | 台 |  | 1 | 0.21629
[11 empty] | 配电箱 |  | AP3 | 台 |  | 1 | 0.21629
[11 empty] | 配电箱 |  | AP4 | 台 |  | 1 | 0.21629
[11 empty] | 配电箱 |  | AP10 | 台 |  | 1 | 0.21629
[11 empty] | 配电箱 |  | AP5 | 台 |  | 1 | 0.30721
[11 empty] | 配电箱 |  | AP6 | 台 |  | 1 | 0.30721
[11 empty] | 配电箱 |  | AP6 | 台 |  | 1 | 0.30721
[11 empty] | 高压成套配电柜 |  | AH1 | 台 |  | 1 | 0.45727
[11 empty] | 高压成套配电柜 |  | AH2 | 台 |  | 1 | 0.45727
[11 empty] | 低压开关柜 |  | AA1 | 台 |  | 1 | 0.66079
[11 empty] | 低压开关柜 |  | AA2 | 台 |  | 1 | 0.66079
[11 empty] | 低压开关柜 |  | AA3 | 台 |  | 1 | 0.66079
[11 empty] | 低压开关柜 |  | AA4 | 台 |  | 1 | 0.51033
[11 empty] | 低压开关柜 |  | AA5 | 台 |  | 1 | 0.51033
[11 empty] | 低压开关柜 |  | AA6 | 台 |  | 1 | 0.51033
III | 公用设备安装费 | [9 empty] | 公用设备安装费 | [5 empty] | 4.3997

## 14特种设备 (hidden)
附表14
特种设备批复与实施对比表
建设单位：中国船舶集团有限公司第七一八研究所 | [20 empty] | 总14表
序号 | 批复情况 | [9 empty] | 实施情况
| 名称 | 功能及组成 | 主要性能指标 | 单位 | 国别 | 数量 | 投资 (万元) | 招标情况 | 布置位置 | 备注 | 名称 | 功能及组成 | 主要性能指标 | 单位 | 国别 | 数量 | 投资 (万元) | 招标情况 | 布置位置 | 特种设备取证情况 | 备注
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
I | 工艺设备 | 0 | 0 | 0 | 0 | 26 | 193 | 0 | 0 | 0 | 工艺设备 | 0 | 0 | 0 | 0 | 26 | 147.6106 | 0 | 0 |  | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
1 | 通风柜 | 0 | 尺寸1800mm*850mm*2350mm;风速0.4-0.5m/s；风量2400m³/h | 套 | 国产 | 22 | 33 | 0 | 0 | 0 | 通风柜 | 0 | 非标 | 套 | 国产 | 22 | 23.8938 | 0 | 0 |  | 0
2 | 振动测试台 | 0 | 尺寸（长×宽）：4m×4m，其高度≥400mm；测试台如有拼接，其整体平整度≤0.1mm，水平度≤0.2mm/m；测试台（铸钢件+钢筋混凝土）固有频率≥70Hz | 套 | 国产 | 4 | 160 | 0 | 0 | 0 | 振动测试台 | 0 | 非标 | 套 | 国产 | 4 | 123.7168 | 0 | 0 |  | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!

## 15成效 (hidden)
附表15
项目建设成效分析表
建设单位：中国船舶集团有限公司第七一八研究所 | [5 empty] | 总15表
序号 | 项目名称 | 子项内容 | 完成情况 | 形成能力 | 建设以来发挥的成效 | 备注
1 | 核电站安全系统项目 | 核电安全设备总装车间 | 已实施 | 本项目建成后，形成年产核电站氨浓度监测仪、消氢系统和安全壳过滤排放系统设备 970台（套）的能力。 | 通过本项目建设，满足了未来一段时期内七一八所核电站氨浓度监测仪、消氢系统和安全壳过滤排放系统设备的生产供货需要。在一定程度上缓解了生产规模不足的压力，实现了批复的建设目标。
|  | 综合楼（夜视仪组装车间） | 已实施
|  | 催化剂及气体检测车间 | 已实施
|  | 消防泵房及水池 | 已实施
|  | 产品性能检测设备 | 已实施